## Phase 1
Phase 1: Backend Monitoring | Done
Day 1: Project Setup + Auth
Initialize backend: | done
npm init -y | done
Install: express, cors, dotenv, prisma | done
Setup folder structure: | done
/routes, /controllers, /models, /services
Setup PostgreSQL:
Create DB
Tables:
users
websites
endpoints
alerts
Integrate Better Auth:
Configure provider (email/GitHub)
Setup session handling
Protect routes (middleware)
Day 2: Website + Endpoint Management
Create API:
POST /websites
GET /websites
POST /endpoints
Fields:
website:
id, name, url, user_id
endpoint:
id, url, website_id
Build frontend form:
Add website
Add endpoints
Day 3: Monitoring Engine (Cron)
Install:
node-cron
axios
Create service:
pingWebsite(url)
pingEndpoint(url)
Setup cron job:
runs every 30–60 sec
Store results in MongoDB:
url
status
responseTime
timestamp
Day 4: Fault Detection System
Write rules:
status ≠ 200 → DOWN
responseTime > 2000 → SLOW
endpoint fail → API_ERROR
Create alerts:
store in PostgreSQL
Fields:
type
severity
message
website_id
Day 5: AI Integration (Simple)
Install:
langchain (or direct API)
Create service:
analyzeAlert(alert, metrics)
Input:
alert type
recent logs
Output:
issue
reason
impact
suggestions
Store AI result with alert
Day 6: Backend APIs for Dashboard
Create APIs:
GET /dashboard
GET /alerts
GET /metrics
Filter by:
user_id (via Better Auth session)
Day 7: Frontend Dashboard (React)
Setup React app
Install:
axios
recharts
Build:
Website list
Status cards (UP/DOWN)
Endpoint list
Day 8: Charts + Alerts UI
Add:
response time chart
uptime %
Alerts panel:
active alerts
severity color
Day 9: AI Insights UI (🔥)
Show AI output:
issue
impact
suggestions
Display only when alert exists

## Phase 2
PHASE 2: Frontend SDK + UX Monitoring | Done
Day 1: Create Frontend SDK
Create file:
sdk.js
Add:
init(config)
send(data) using navigator.sendBeacon
Day 2: Capture JS Errors
Use:
window.onerror
Send:
message
stack
page URL
Day 3: Track API Failures
Override:
window.fetch
Capture:
failed requests
slow responses
Day 4: Track Page Load
Use:
performance.timing
Send:
load time
Day 5: Backend Endpoint for Frontend Data
Create:
POST /frontend-log
Store in MongoDB:
type
page
error
timestamp
Day 6: Frontend Dashboard (UX Tab)
Add new section:
“User Experience”
Show:
JS errors
slow pages
failed API calls